## Week 12-9
TEST THE WEB FORWARD
| Date | Venue | Speakers | Experts | Topics/Schedule | Partner/Sponsors | Budget
12 Weeks from event: Start research and outreach | Choose three to four potential dates. Is there a larger convention on a related subject or that has the same target audience you can piggyback on? TPAC etc. | What kind of attendanece can you expect in your city? What is your target number? Keep in mind you can expect a 50-60% dropoff rate for a free event. | Reach out to speakers | Reach out to experts | What is the theme? Does it allign with your speakers/experts available? | Reach out to partners about sponsorship interest | Estimate the costs
11 Weeks from event: Gather the details | Are there conflicting or popular events? Check Meetup.com, Eventbrite.com, Facebook.com, Lanyard, & local community calendars. Don't forget to consider holidays, school breaks, and sporting events. | What venues are available on your target dates that can accommodate your event size? | Are there speakers in your area interested in participating? Out of area?What is their expertise/topic? | Are there experts in your area interested in participating? Out of area? What is their expertise/topic? | Can the topics be covered in the time allowed? | Sponsorship opportunities: Venue, catering, hosting, internet, speakers/experts, banners etc. | What is your budget? What is not covered?
10 Weeks from event: Refine the details | What dates work for the speakers, experts, partners/sponsors? | Complete venue checklist for comparison: Location, public transportation, parking, internet, A/V, catering options, distance to hotels etc. | Can they commit to TestTWF? | Can they commit to TestTWF? | Topics/Schedule draft | Can they commit to TestTWF? | What can the sponsors cover?
9 Weeks from event: Finailze the plan | Final Date | Final Venue | Final Speakers | Final Experts | Final Topics/Schedule | Final Sponsors | Final Budget

## Week8-5
TEST THE WEB FORWARD
| Registration | Catering | Swag, Raffle, Signs | Marketing/Promotion | Venue | Speakers | Experts | Topics/Schedule | Partners/Sponsors
8 Weeks from event | Determine registration method and requirments. | Research catering options | What swag is needed? What are the sponsors taking care of? What signs do you need to print? Badges? | Communication and promotion plan. Loop in partners, sponsors, speakers, and experts. | Contract & deposit. Do you need additional insurance? Loop in partner if they are sponsoring. Check with local hotels if you can negoiate a group rate. | Distribute the speaker kit and make sure they understand the expectations. Ask for Bio. | Send them their expectations. Ask for Bio. | Refine topics & schedule if necessary. | Finalize sponsorships with partner.
7 Weeks from event | Registration setup and go live. Send out registration communication to speakers, experts, etc. | Breakdown costs to sponsors | Collect all the assets for the swag and signage- art, logos etc. and send to responsible parties. | Post event to TestTWF.org, Blog, tweet, Facebook, Lanyard.com, Meetup.com, Linkedin.com | Finalize A/V details | Ask speakers to promote TestTWF. | Ask experts to promote TestTWF. | Refine topics & schedule if necessary. | Finalize sponsorships with partner.
6 Weeks from event | What are the numbers? Is it on track? | Sample menu | T-shirts and stickers should be sent to the vendor. | Continue promoting. Remember that for free events you need to secure double the number of registrants due to 50-60% dropoff. | Check status | Check in on speakers and progress of presentation. Have they registered and booked travel? | Check in on experts. Have they registered and booked travel? | Refine topics & schedule if necessary. | Check on sponsorship, provide shipping information for swag or final invoice/billing.
5 Weeks from event | What are the numbers? Is it on track? Are there any issues with the systems? Are you getting a lot of questions? | Finalize menu and pay desposit | Check swag samples & and approve proof. | Re-evalute marketing and promotion. What are the registration numbers? | Pay remaining amount on venue. | Send a calendar invite for their participation. Include all details of the event. | Send a calendar invite for their participation. Include all details of the event. | Freeze Topics/Schedule. Make sure to post any chnages to registration as well as website. | Send a calendar invite for their participation. Include all details of the event.

## Week 4-1
TEST THE WEB FORWARD
| Registration | Catering | Swag, Raffle, Signs | Marketing/Promotion | Venue & Volunteers | Speakers | Experts | Partners/Sponsors
4 Weeks from event | Check social media channels to see what the buzz is. Ask speakers, experts, and sponsors to do another push to their communities and followers. | N/A | All swag should be in production. | Check social media channels to see what the buzz is. Ask speakers, experts, and sponsors to do another push to their communities and followers. | Organize volunteers for staffing registration desk, setup, and tear down. | Speakers should have presentation comeplete. Send slide deck off for translations if necessary. | N/A | At this point there shouldn't be much left to do other then communicate details of the event and work on promotion.
3 Weeks from event | How many registered? | N/A | Make sure everything is on schedule- tracking numbers. | If you still need registrations, start looking to outside channels to promote. | Assign tasks to volunteers. | Are deck translations complete? | N/A | Make sure everyone is happy with their sponsorship!
2 Weeks from event | How many registered? | Check in with caterer and submit final numbers. Make sure they know venue details for delivery/setup. | Signs and posters should be sent to printer. Make sure there haven't been any changes to the shedule. | Check social media channels to see what the buzz is. Ask speakers, experts, and sponsors to do another push to their communities and followers. | Check with venue to make sure all is on track with shipping, setup, vendors, teardown etc | Check in on speakers. Make sure they know to arrive early for tech check. | Check in on experts. | Check in on sponsors. Make sure they there sponsorship is listed in signage that is sent to printers this week.
1 Weeks from event | Send out reminder email to attendees. Collect attendee list to print badges. | Confirm final details. | Collect registration list and print attendee badges. Make sure to have blank badges onsite for late registrations. All swag and signage should be on track to be delivered this week. | Do one last push if your numbers are still low! | Send calender invite/email to all volunteers with their duties outlined. | Check in on speakers. If traveling make sure they will arrive on time. Reiterate the time they need to show up. | Check in on experts. If traveling make sure they will arrive on time. Reiterate the time they need to show up. | Make sure everyone is happy with their sponsorship!

## 3 days
TEST THE WEB FORWARD
| Registration | Catering | Swag, Raffle, Signs | Marketing/Promotion | Venue | Speakers & Experts | Volunteers | Partners/Sponsors
3 Days before event! | If you haven't sent out the reminder email to the attendees, do so today. Check you numbers and report any large increase or decrease to catering. Collect additional names that need badges printed. Release names from the waiting list if you have cancellations. | Communicate any changes to caterer. | Everthing should have arrived. If not, track it down. Print additional badges. | Check social media channels to see what the buzz is. Make sure you are responding to tweets etc. | Communicate any changes to venue. | Check in, deal with any issues that may have come up last minute. | Are your volunteers still on board to help? | Do you have happy sponsors?

## 2 Days
TEST THE WEB FORWARD
| Registration | Catering | Swag, Raffle, Signs | Marketing/Promotion | Venue | Speakers & Experts | Volunteers | Partners/Sponsors | Contact List
2 Days before event! | Answer attendee questions. Release more names from waitlist if there are cancellations. | Communicate any changes to caterer. | Everthing should have arrived. If not, track it down. Print additional badges. | Check social media channels to see what the buzz is. Make sure you are responding to tweets etc. | Communicate any changes to venue. | Check in, deal with any issues that may have come up last minute. | Print out your volunteer checklist. | Do you have happy sponsors? | Collect and generate a contact list for all involved individual- speakers, experts, volunteers, security, janitorial/facilities, catering. This should include email, and mobile phone.

## 1 Day
TEST THE WEB FORWARD
| Registration | Catering | Swag, Raffle, Signs | Marketing/Promotion | Venue | Speakers & Experts | Volunteers | Partners/Sponsors | Contact List
1 Day before event! | Answer attendee questions. Release more names from waitlist if there are cancellations. | Communicate any changes to caterer. | Print additional badges. Organize your swag! Sort the t-shirt sizes and set some aside for the speakers, experts, volunteers, and other important people. | Check social media channels to see what the buzz is. Make sure you are responding to tweets etc. | If you can drop off items one day ahead, do so. Do an onsite venue walk through. | Check in, deal with any issues that may have come up last minute. | Have volunteers completed any pre-event tasks? | Do you have happy sponsors? | Print your contact list.

## Event Day 1
TEST THE WEB FORWARD
Before: Setup (3 hours before start)
Registration Table | Badges should be assembled and in alphabetical order. Set aside speakers, experts, volunteers. Make sure to have a few blank badges. | Print current attendee list. Make several copies | T-shirts are organized by size and gender. Set aside speakers, experts, volunteers | Set out other swag- stickers etc. | Raffle - set out raffle tickets or signup method for raffle.
A/V | Is A/V setup. Speakers need to do a tech check. | If you are running A/V yourself, make sure to have extra cables, adapters, batteries etc. | Welcome slide with wifi info, agenda, pre-survey link etc. | Background music till start
Venue | Check tables and chairs setup properly | Check power | Check internet. Is wifi working? | Put up signage | Catering- are the things the caterers need setup? Tables, dinerware, napkins, utensils, cups etc. | Are drinks setup? Water, coffee, other | Check with janitorial that they will empty trash after dinner and/or that you know where the bin is.
Organizer/Host | Have a "staff" meeting and make sure all volunteers know their duties and have the materials they need. Make sure they also know saftey/emergency exits and procedures. | When speakers and experts show up get them badges and tshirts. Take speakers to do A/V check | Confirm catering will be on time | Is the MC prepared. Does he/she have a script, name pronunciation etc. | Translator on hand to answer questions and assist with communication.
During: Event
Registration | 2-3 people should be working to check in attendees and hand out swag and raffle tickets. | Check off attendees from list or check in via registration system so you can track it later. | Will need local language speaker(s) on hand or handling registration
Organizer/Host | Make introductions and facilitate networking before MC welcome | Monitor registration for problems. If there are any delays etc then delay start | Cue MC when ready | Cue MC when food and drinks are ready | Be accessable to deal with problems!
MC & Speakers | MC- welcome & opening statement | Thank sponsor if they are hosting the event | MC- point out experts (shirts or badges) | MC- point out translators if you have them | MC- Indroduce speakers & keep them on time | MC- close day one, remind about start time.
Social Media & Videography | Monitor hashtag | Tweet and post pics | Local language social media? | Take video/pics during event
Drinks/Food | Caterer or volunteers set up food. Make sure special meals are properly labeled. | Voluteers check in halfway to keep food/beverages tidy, clean and stocked. Make more coffee etc. | If event goes late, do another beverage check a couple hours after dinner.
After: Shutdown
Organizer/Host | Politely usher people out that are lingering. | Do a venue walkthorugh to make sure no guests are in areas they shouldn't be. | Make sure speakers, experts, and volunteers know when to show up on Day 2.
Registration | Make sure registration desk is in order for next day | Clean up swag and set more out for morning
A/V | Shutdown system
Cleanup | Check for forgotten items by attendees | Remember to check all rooms. | In general, make sure things are orderly for next day. Push in chairs, make sure extensions cables are still taped down etc.
Signage | Are signs still up and/or do some need to be changed for Day 2

## Event Day 2
Before: Setup (1 hour before start)
Registration Table | Badges should be assembled and in alphabetical order. Make sure to have a few blank badges. | Make sure attendee list is still available. | T-shirts are organized by size and gender. Set aside speakers, experts, volunteers | Set out other swag- stickers etc. | Raffle - set out raffle tickets or signup method for raffle.
A/V | Is A/V setup. Do a quick tech check. | Welcome slide with wifi info, agenda, pre-survey link etc. | Background music till start
Venue | Check tables and chairs setup properly. Did janitorial clean all rooms and restrooms. | Check power | Check internet. Is wifi working? | Catering- Breakfast should be setup before registration opens. Any special meals should be properly labled. | Water, coffee & tea setup | Check with janitorial that they will empty trash after lunch and/or that you know where the bin is.
Organizer/Host | Have a "staff" meeting and make sure all volunteers know their duties and have the materials they need. Make sure they also know saftey/emergency exits and procedures. | Have the speakers and experts arrived early. | Confirm catering will be on time | Is the MC prepared. Does he/she have a script, name pronunciation etc. | Translator on hand to answer questions and assist with communication.
During: Event
Registration | 2-3 people should be working to check in attendees and hand out swag and raffle tickets. | Check off attendees from list or check in via registration system so you can track it later. | Will need local language speaker(s) on hand or handling registration | After MC welcomes Day 2, you only need one person staffing registration.
Organizer/Host | Make introductions and facilitate networking before MC welcome. | Monitor registration for problems. If there are any delays etc then delay start. | Cue MC when ready | Cue MC when food and drinks are ready | Be accessable to deal with problems!
MC & Speakers | MC- Welcome & opening statement Day 2 | MC- Indroduce speakers & keep them on time. Also call out experts. | MC -Announce winners of raffle. | MC- closing statement, thanks all involved for great event.
Social Media & Videography | Monitor hashtag | Tweet and post pics | Local language social media? | Take video/pics during event
Drinks/Food | LUNCH: Caterer or volunteers set up food. Make sure special meals are properly labeled. | Voluteers check in halfway to keep food/beverages tidy, clean and stocked. | DINNER/DRINKS: Caterer or volunteers set up food. Make sure special meals are properly labeled. | Voluteers check in halfway to keep food/beverages tidy, clean and stocked.
After: Shutdown
Organizer/Host | Politely usher people out that are lingering. | Do a venue walkthorugh to make sure no guests are in areas they shouldn't be. | Thank speakers, experts, and volunteers!
A/V | Shutdown system
Cleanup | Check for forgotten items by attendees. Remember to check all rooms. | Clean up registration and put away swag. | Make sure everything is left in good condition and put away.
Signage | Remove signs