## Slide 1: WoT Virtual F2F Charter Discussion
Michael McCool
26 October 2021

## Slide 2: Agenda
Schedule revisions
  Needed prior to asking for 6mo extension to WG charter
  Need to consider deadlines for all deliverables using milestone calculator
WG Charter Extension
  Resolution needed – including above schedule revisions
Proposed IG Charter renewal
  Discuss revisions
Proposed WG Charter renewal
  Discuss revisions and deliverables

## Slide 3: Schedule Constraints
Current end of WG charter is Jan 31
6mo extension gives July 31
Milestone tool gives the following:
  REC: July 26
  PR: June 21
  CR: May 5
  FPWD: Jan 13 (may be relevant if we want to publish a TD 2.0 spec)
Prudence backs off PR/CR by 2mo to allow for "review slip":
  PR: mid-April
  CR: mid-March
  Implementations, testfest: mid-Feb; spec feature freeze/early review: Dec 31

## Slide 4: Revised Plan for Normative Deliverables
Thing Description
  1.1
    May need to rollback some things for KISS, compatibility (e.g. optional forms)
    Decide on rollback features by end of Nov
    Aim for feature freeze Dec 15, to give time for Profiles to catch up by Jan 31
  2.0
    FPWD deadline is Jan 13
    Probably not feasible, will have to defer to next charter
Architecture
Discovery
Profiles